## Sheet3
Key | Issue Type | Parent | Summary | Status | Assignee | Sprint | Start date | Due date
SQRTS3-1 | Epic |  | Environment Setup | Done |  |  | 2025-02-14 | 2025-03-23
SQRTS3-3 | Task | SQRTS3-1 | ReactJs Repo Setup | Done | Yadana Su Thin | SQRTS3 Sprint 0 | 2025-02-14 | 2025-02-27
SQRTS3-4 | Task | SQRTS3-1 | Mobile Env Setup | Done | Min Than Zaw | SQRTS3 Sprint 0 | 2025-02-14 | 2025-02-27
SQRTS3-5 | Task | SQRTS3-1 | Cloud Env Setup | Done | Randall Ong | SQRTS3 Sprint 0 | 2025-02-14 | 2025-02-27
SQRTS3-2 | Task | SQRTS3-1 | SpringBoot Repo Setup | Done | Yew Hoon Peh | SQRTS3 Sprint 0 | 2025-02-14 | 2025-02-27
SQRTS3-45 | Task | SQRTS3-1 | Local Env Setup & Library Update for Repos | Done | Balaji Sivaprakasam | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-10 | Epic |  | Initial Research & Documentation | Done |  |  | 2025-02-14 | 2025-04-06
SQRTS3-90 | Task | SQRTS3-10 | Update Threat Modelling | Done | Randall Ong | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-72 | Task | SQRTS3-10 | Cybersecurity Act Research | Done | Randall Ong | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-17 | Task | SQRTS3-10 | PDPA Research | Done | Randall Ong
SQRTS3-32 | Task | SQRTS3-10 | Create user stories for security requirements | Done | Yadana Su Thin | SQRTS3 Sprint 0 | 2025-02-14 | 2025-02-27
SQRTS3-42 | Task | SQRTS3-10 | Implement Least Privilege Access | Done | Yew Hoon Peh | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-43 | Task | SQRTS3-10 | Enforce Fail-Secure Defaults | Done | Yew Hoon Peh | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-6 | Task | SQRTS3-10 | Perform Threat Modelling | Done | Randall Ong | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-7 | Task | SQRTS3-10 | As a member of the development team, I want to know the laws, regulations, security policies that are applicable to public transport and payments systems so that the team knows the cybersecurity standards that QRPass must meet | Done | Randall Ong | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-8 | Task | SQRTS3-10 | Create evil user stories | Done | Randall Ong | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-65 | Task | SQRTS3-10 | Study AWS Cognitoâ€™s Integration with AWS API Gateway for Authentication | Done | Min Than Zaw | SQRTS3 Sprint 0 | 2025-02-14 | 2025-02-27
SQRTS3-66 | Task | SQRTS3-10 | Study AWS Cognito authentication mechanisms (OAuth, JWT, OpenID Connect, MFA, etc.) | Done | Min Than Zaw | SQRTS3 Sprint 0 | 2025-02-14 | 2025-02-27
SQRTS3-67 | Task | SQRTS3-10 | Study AWS Cognito integration with web application and mobile application | Done | Min Than Zaw | SQRTS3 Sprint 0 | 2025-02-14 | 2025-02-27
SQRTS3-68 | Task | SQRTS3-10 | Study AWS Cognitoâ€™s User Authentication Flow social login (Google, Facebook, Apple) | Done | Yadana Su Thin | SQRTS3 Sprint 0 | 2025-02-14 | 2025-02-27
SQRTS3-73 | Task | SQRTS3-10 | Payment Services Act Research | Done | Randall Ong
SQRTS3-75 | Task | SQRTS3-10 | Business Continuity Plan (BCP) | Done | Yew Hoon Peh | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-76 | Task | SQRTS3-10 | Disaster Recovery Plan (DRP) | Done | Yew Hoon Peh | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-81 | Task | SQRTS3-10 | Create Manual For SAST Configuration | Done | Min Than Zaw | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-84 | Task | SQRTS3-10 | Architecture diagrams for Physical Architecture, IaC, and DevSecOps | Done | Min Than Zaw | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-89 | Task | SQRTS3-10 | Vulnerability Scan of apk file using Mobsf | Done | Yew Hoon Peh | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-11 | Epic |  | Evil User Stories | Done
SQRTS3-14 | Task | SQRTS3-11 | Extracting traffic information | To Do
SQRTS3-15 | Task | SQRTS3-11 | Altering live ridership information | To Do
SQRTS3-18 | Epic |  | Security Requirements | To Do |  |  | 2025-02-24 | 2025-05-05
SQRTS3-88 | Task | SQRTS3-18 | Add Cookie Policy, Data Privacy and Terms and Conditions | Done | Yadana Su Thin | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-59 | Task | SQRTS3-18 | Implement Authn & Authz Management Process for JWT & MFA in Backend | Done | Yadana Su Thin | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-54 | Task | SQRTS3-18 | Authentication & Authorization Management Process for JWT & MFA in Web and Mobile Apps | Done | Min Than Zaw | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-58 | Task | SQRTS3-18 | Integrated with Cognito for RBAC | Done | Min Than Zaw | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-62 | Task | SQRTS3-18 | Implement Secure Storage in Mobile App | Done | Min Than Zaw | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-77 | Task | SQRTS3-18 | As a system admin, I will create an operational user account and define the role in web app | Done | Yadana Su Thin | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-78 | Task | SQRTS3-18 | The system needs to implement a new feature to comply with PDPA in the web app | Done | Yadana Su Thin | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-82 | Task | SQRTS3-18 | As a commuter logs in with an existing social media account, the system needs to implement OAuth in the web application | Done | Min Than Zaw | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-83 | Task | SQRTS3-18 | The system needs to implement a new feature to comply with PDPA in app | Done | Min Than Zaw | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-22 | Task | SQRTS3-18 | As a user, I want to log in securely using my credentials, so that my account and personal information remain protected. | Done | Min Than Zaw | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-25 | Task | SQRTS3-18 | As a system, I want to generate QR codes that are digitally signed, so that they cannot be tampered with or forged. | Done | Yadana Su Thin | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-27 | Task | SQRTS3-18 | As a system, I want to limit the number of API requests per user, so that automated bots cannot perform brute-force attacks on QR validation. | Done | Yadana Su Thin | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-28 | Task | SQRTS3-18 | As a system, I want to track all login attempts and API access logs, so that I can detect and investigate security threats. | Done | Min Than Zaw | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-31 | Task | SQRTS3-18 | As a AFC staff, I want to scan a QR code and validate it securely, so that only valid tickets grant access to the transportation system. | Done | Min Than Zaw | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-79 | Task | SQRTS3-18 | SAST Configuration | Done | Yadana Su Thin | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-80 | Task | SQRTS3-18 | Set up Snyk and sonarqubecloud | Done | Min Than Zaw | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-85 | Task | SQRTS3-18 | Create Ticket Detail For QR Validator | Done | Yadana Su Thin | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-87 | Task | SQRTS3-18 | Update UI in Home, View User, Generate Ticket, Buy Ticket | Done | Yadana Su Thin | SQRTS3 Sprint 2 | 2025-03-10 | 2025-03-23
SQRTS3-93 | Task | SQRTS3-18 | Vulnerability Scan of apk file | Done | Yew Hoon Peh | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-101 | Task | SQRTS3-18 | Update Threat Modelling - DREAD Score | Done | Balaji Sivaprakasam | SQRTS3 Sprint 4 | 2025-04-07 | 2025-04-20
SQRTS3-12 | Task | SQRTS3-18 | OWASP Zap Tool Enviroment Setup | Done | Yadana Su Thin | SQRTS3 Sprint 5 | 2025-04-21 | 2025-05-05
SQRTS3-26 | Task | SQRTS3-18 | DAST Reports for microservices and web application | Done | Yadana Su Thin | SQRTS3 Sprint 5 | 2025-04-21 | 2025-05-05
SQRTS3-33 | Epic |  | Identity Management | To Do |  |  | 2025-02-24 | 2025-05-05
SQRTS3-34 | Task | SQRTS3-33 | As a user, I want to log in to QRPass using my Google account, so that I don't have to remember a separate username and password. | Done | Yadana Su Thin | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-38 | Task | SQRTS3-33 | As a new user, I want to automatically create a QRPass account when I log in via Google, so that I donâ€™t have to manually sign up. | Done | Yadana Su Thin | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-40 | Task | SQRTS3-33 | As a user, I want to log out from QRPass and ensure my session is also revoked from Google, so that my authentication token is no longer valid. | Done | Min Than Zaw | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-41 | Task | SQRTS3-33 | As a security administrator, I want to enforce multi-factor authentication (MFA) for admin users logging in via OIDC, so that high-privilege accounts remain secure. | Done | Min Than Zaw | SQRTS3 Sprint 1 | 2025-02-24 | 2025-03-09
SQRTS3-16 | Task | SQRTS3-33 | AWS Lamda Authorizer and API Gateway Configuration | Done | Yadana Su Thin | SQRTS3 Sprint 5 | 2025-04-21 | 2025-05-05
SQRTS3-29 | Task | SQRTS3-33 | Amazon Verified Permissions Configuration with Cognito | Done | Min Than Zaw | SQRTS3 Sprint 5 | 2025-04-21 | 2025-05-05
SQRTS3-48 | Task | SQRTS3-33 | AWS Lamda Authorizer Configuration | Done | Yadana Su Thin | SQRTS3 Sprint 5 | 2025-04-21 | 2025-05-05
SQRTS3-35 | Epic |  | DevSecOps Pipeline Setup | Done | Min Than Zaw
SQRTS3-46 | Epic |  | Database Encryption | To Do |  |  | 2025-03-24 | 2025-04-20
SQRTS3-49 | Task | SQRTS3-46 | DB Encryption Implementation | Done | Balaji Sivaprakasam | SQRTS3 Sprint 3 | 2025-03-24 | 2025-04-06
SQRTS3-47 | Task | SQRTS3-46 | Update code to connect to the new encrypted DB | Done | Balaji Sivaprakasam | SQRTS3 Sprint 4 | 2025-04-07 | 2025-04-20
SQRTS3-50 | Task | SQRTS3-46 | Documentation & Compliance | Done | Balaji Sivaprakasam | SQRTS3 Sprint 4 | 2025-04-07 | 2025-04-20
SQRTS3-51 | Task | SQRTS3-46 | Encrypted DB Deployment at AWS | Done | Balaji Sivaprakasam | SQRTS3 Sprint 4 | 2025-04-07 | 2025-04-20
SQRTS3-52 | Epic |  | Encrypt/tokenize data in transit between client and back end | To Do |  |  | 2025-04-21 | 2025-05-05
SQRTS3-53 | Task | SQRTS3-52 | TLS Setup | To Do
SQRTS3-55 | Task | SQRTS3-52 | Mutual TLS | To Do
SQRTS3-56 | Task | SQRTS3-52 | Prod Deployment | Done | Min Than Zaw | SQRTS3 Sprint 5 | 2025-04-21 | 2025-05-05
SQRTS3-57 | Epic |  | Mobile API key authentication | To Do
SQRTS3-60 | Task | SQRTS3-57 | Secure Transmission of API Keys | Done | Min Than Zaw
SQRTS3-61 | Task | SQRTS3-57 | API Key Rotation Mechanism | Done | Yadana Su Thin
SQRTS3-63 | Task | SQRTS3-57 | Monitor API Key Usage and Generate Alerts | Done | Min Than Zaw
SQRTS3-64 | Task | SQRTS3-57 | Document Authn & Authz Management Process for JWT & MFA | Done | Yadana Su Thin
SQRTS3-69 | Epic |  | Business Continuity | To Do
SQRTS3-71 | Task | SQRTS3-69 | Establish Business Continuity Plan (BCP) | To Do
SQRTS3-70 | Task | SQRTS3-69 | Establish Disaster Recovery (DR) plan | To Do
SQRTS3-86 | Epic |  | Apply security features to the app | Done | Min Than Zaw |  | 2025-04-18 | 2025-04-25